# Doc. Code: BFUG_PL_AM_26_13b

# ANNEX 1 – ROADMAP FOR BFUG CONSULTATION FOR THE THIRD BOLOGNA POLICY FORUM STATEMENT

| Drafting phase | When? | Who? |
| --- | --- | --- |
| Draft 0 of the BPF Statement is circulated to the IO WG members | 1 October 2011 | Romania and the BFUG Secretariat |
| Discussion of the BPF Statement | 9 November 2011 | IO WG report during its Bucharest meeting |
| Integration of the IO WG members feedback | 10 November – 11 December 2011 | Romania and the BFUG Secretariat |
| Circulation of Draft 1 of the BPF Statement to the BFUG members and the national contact persons for their written feedback | 12 December 2011 | Romania and the BFUG Secretariat |
| Deadline for receiving written comments from BFUG members and national contact persons to Draft 1 of the BPF Statement | 20 January 2012 | BFUG members and national contact persons |
| Integrating the written comments and preparing Draft 2 of the BPF Statement | 21 – 30 January 2012 | Romania and the BFUG Secretariat |
| Circulating Draft 2 of the BPF Statement to the IO WG members | 1 February 2012 | Romania and the BFUG Secretariat |
| Discussing Draft 2 of the BPF Statement | 10 February 2012 | IO WG during its Rome meeting |
| Integrating the comments of the IO WG and preparing Draft 3 of the BPF Statement | 11 -19 February 2012 | Romania and the BFUG Secretariat |
| Circulating Draft 3 of the BPF Statement to the BFUG members and the national contact persons | 20 February 2012 | Romania and the BFUG Secretariat |
| Deadline for receiving written comments to the Draft 3 of the BPF Statement | 3 March 2012 | BFUG members and the national contact points |
| Integrating the comments of the BFUG members and the national contact persons and preparing the Final Draft of the BPF Statement | 4-10 March 2012 | Romania and the BFUG Secretariat |
| Circulating the Final Draft of the BPF Statement to the BFUG members for endorsement and the national contact points | 13 March 2012 | Romania and the BFUG Secretariat |
| Endorsing the Final Draft of the BPF Statement by the BFUG | 19-20 March 2012 | BFUG |
| Adoption of the BPF Statement | 27 April 2012 | BPF participants |