# Annex 2

# Tentative roadmap for consultations related to the Third edition of the Bologna Policy Forum (BPF3)

| Timeline | Consultation activity | Result |
| --- | --- | --- |
| Sept – Oct 2010 | General consultation with the BFUG and national contact points (NCP) for the themes of the BPF3 | Overview of themes proposed for BPF3 |
| 18 January 2011 | IO WG meeting Vienna: Input for programme/ content of BPF3 (discussion on the feedback received from the NCP) Update on IPN and discussion on roundtable for enhancing European-level promotion Prepare update for BFUG Proposals for the overarching BPF3 theme and possible sub-themes | Proposal for a limited number of BPF3 themes to the BFUG Update for the 17-18 March 2011 BFUG meeting in Gödöllő, Hungary Overarching BPF3 theme proposals |
| 17-18 March 2011 | BFUG meeting Gödöllő, Hungary Decision on the proposed overarching BPF3 theme and endorsing the latest version of the BPF agenda and the IO WG update | Endorsement of the overarching theme and agenda of the BPF3 |
| April – May 2011 | Informing the NCP about the BFUG decisions (BPF3 overarching theme and agenda) Consultation with the NCP on the BPF3 shortlisted sub-themes, ideas for possible speakers and the BPF3 statement | Feedback on shortlisted BPF3 sub-themes, ideas for possible speakers and for the BPF3 statement |
| 19 May 2011 | IO WG meeting Brussels Discussing the feedback received on the sub-themes and possible speakers Discussing the main aims and structure of the BPF3 statement Updates regarding the IPN Discussing the final report of the IO WG to the BFUG | Revised sub-themes and list of possible speakers Proposal for the main points of the BPF3 statement Structure of the IO WG report to the October 2011 BFUG in Cracow |
| June – Sept 2011 | Circulation of possible changes made in the IO WG meeting to the sub-themes, the BPF3 agenda and speakers, as well as the main points of the BPF3 statement | Possible additional feedback from NCP |
| 13-14 October 2011 | BFUG meeting Cracow Endorsing sub-themes and keynote speaker proposals Endorsing the main points for the BPF3 statement | Sub- themes and speaker proposals BPF3 statement main points |
| 9 November 2011 | IO WG meeting (Bucharest) BPF3 draft statement discussion BPF3 background materials | BPF3 draft statement BPF3 background materials |
| October – December 2011 | Consulting the NCP on BPF3 draft statement | Feedback on BPF3 statement |
| 18-19 January 2012 | BFUG meeting Copenhagen Discussions on BPF3 statement, together with the received feedback Endorsing the Manual for the BPF3 (MBPF) | BPF3 statement new draft Manual for the BPF3 (MBPF) |
| January – February 2012 | Consultation with the NCP on the BPF3 draft statement and circulating the MBPF | Feedback on the BPF3 statement |
| January – February 2012 | Possible IO WG meeting (location tbc) BPF3 format and background papers review BPF3 draft statement discussion | BPF agenda – detailed BPF statement new draft and background papers |
| 21-22 March 2012 | BFUG meeting Copenhagen Final endorsement of the BPF3 detailed agenda Additional feedback on BPF3 statement | BPF3 detailed agenda Possible changes to the BPF3 statement |
| End of March-April 2012 | Final circulation to the NCP of the final detailed agenda and the final statement before its discussion in the BPF3 | Announcements of possible proposals for amending the BPF3 statement |
| 26-27 April 2012 | Third Bologna Policy Forum (BPF3) | 3rd BPF Statement Parallel sessions reports |