Timeline for the production of the integrated report

on the implementation of the Bologna Process

| 2010 | Ongoing Eurostat data collection | Eurostudent data collection |
| --- | --- | --- |
| 21 January | WG Reporting: Approve draft outline of the integrated report and timeline to be presented to the BFUG in Madrid on 18-19 February 2010. |  |  |
| 18-19 February | BFUG: approval of main orientation of the integrated report & the timeline for preparing it |  |  |
| February – August | Definition of indicators and development of questionnaire by Eurydice, Eurostat and Eurostudent |  |  |
| June (exact date tbc) | WG Reporting: discussion and preliminary approval of indicators and structure of the integrated report |  |  |
| 24-25 August | BFUG: approval of indicators, structure of the integrated report and comments to questionnaire |  |  |
| September-December | Pre-test of questionnaire by Eurydice |  |  |
| November (exact date tbc) | WG Reporting: approval of questionnaire prepared by Eurydice |  |  |
| 2011 |  |  |
| January/February (exact date tbc) | BFUG: approval of questionnaire prepared by the data collectors |  |  |
| February – April | Data collection by Eurydice through the questionnaire which will be filled by BFUG representatives in consultation with national stakeholders. Data collection by Eurostat of statistical information from countries of the EHEA not participating in the regular data collections |  |  |
| May- November | Analysis of material, drafting of integrated report, integrating data from Eurostat, Eurostudent and Eurydice |  |  |
| October (exact date tbc) | WG Reporting: Discussion of the draft integrated report and development of conclusions |  |  |
| End of year | Draft integrated report and conclusions to be sent to BFUG |  |  |
| 2012 |  |  |
| January (exact date tbc) | BFUG: discussion of draft integrated report and of the conclusions by the WG Reporting in October |  |  |
| March | Print-ready electronic version of the integrated report provided to BFUG |  |  |
| 27-28 April | Presentation of final integrated report to the ministerial conference |  |  |