# Working Group to support the implementation of the Roadmap for San Marino’s accession to the EHEA - Update to the Bologna Follow-up Group

## Overview of the developments

The purpose of the working group is to follow up the San Marino Roadmap together with the Sammarinese authorities and to assist the Sammarinese authorities in implementing the roadmap and in developing specific policy areas. The working group on San Marino Roadmap also assists in peer-learning activities and facilitates cooperation. The WG will present the final report to the BFUG on the state of implementation of the roadmap by the beginning of 2024.

WG has now held two meetings (May and November 2021). The main developments are as follows:

* San Marino is willing to further develop the higher education system along the lines agreed in the Roadmap and has established an implementation plan for the reforms and prepared a first draft for the NQF.
* The working group has outlined a working plan for its work. The work plan builds of the Roadmap and on the implementation plans of Sammarinese authorities.
* Peer support and peer learning activities have started between working group members, Sammarinese authorities and representatives of University of San Marino focused on the implementation of the key commitments and higher education governance.
* The working group has exchanged views on the implementation of reforms with university management, staff and students.
* The working group agreed to organize further peer support sessions on quality assurance and on university governance models in addition to regular working group meetings.

## 2. Timetable and work plan

The work plan builds on timelines of the Roadmap and on the implementation plans of Sammarinese authorities. The roadmap outlines two sets of actions. A first set concerns the launching of implementation measures, for which the deadline is generally 1 June 2021. A second set of actions concerns the completion of these actions by 1 November 2023.

#### Qualifications framework

San Marino will develop a National Qualifications Framework compatible with the QF-EHEA, incorporating a learning outcomes approach, and proceed to self-certifying the NQF against the Overarching Framework of Qualification of the EHEA (QF-EHEA) with the participation of foreign experts.

|  |  |  |
| --- | --- | --- |
| **Time** | **Roadmap** | **San Marino’s implementation plan** |
| By 1 June 2021 | Establish a timetable for this work and identify a national steering group and launch work on the NQF by 1 June 2021.   * flexible learning paths * specify the place of certain qualifications | Working group on QF by the Ministry has been established   * involvement of all stakeholders * A national point of coordination for the independent evaluation of the self-certification of the NQF against the EHEA-QF has been established under Ministry of Education and the involvement of San Marino Job Centre * Co-operation with Italy |
| November 2021 |  | First draft of the law |
| By 1 June 2022 |  | Parliament’s first discussion of the law |
| By 1 November 2023 | Complete the NQF, including self-certification | Participation of foreign experts in the development of the NQF and establishment of the self-certification |

#### Quality assurance

San Marino will develop a plan for quality assuring higher education in San Marino in accordance with the Standards and Guidelines for Quality Assurance in the European Higher Education Area (ESG).

|  |  |  |
| --- | --- | --- |
| **Time** | **Roadmap** | **San Marino’s implementation plan** |
| By 1 June 2021 | Develop a timetable for establishing quality assurance arrangements.   * clarify the roles and functions of the IAB * engage in the activities and professional networks of ENQA | Independent Assessment Body (IAB) at the University of San Marino has recently been established to develop the guidelines of an initial and very streamlined internal QA System. |
| By 1 June 22 |  | Definition of guidelines for internal quality assurance |
| By 1 November 2023 | Conclude an agreement with a foreign quality assurance agency  Legislation establishing the basis for conducting QA in conformity with the ESG. | Conclude an agreement with a foreign quality assurance agency. |

#### Recognition of qualifications

San Marino will give due consideration to the introduction of the recognition of prior learning, including informal and non-formal learning, as part of the implementation of the ECTS User’s Guide.

|  |  |  |
| --- | --- | --- |
| **Time** | **Roadmap** | **San Marino’s implementation plan** |
| By 1 June 2021 | Establish a timetable for the introduction of the recognition of prior learning. | First draft of the document for the recognition of qualifications based on the evaluation report related to the modifications which are needed |
| By 1 September 2022 |  | Implementation of measures in the University guidelines |
| By 1 November 2023 | Implement measures to the extent they do not require modifying legislation and introduce any required legislation for submission to Parliament |  |

#### Higher education governance

San Marino will implement the principles of the EHEA, as expressed in successive declarations and communiqués adopted by the Ministers, concerning student and staff participation, with voting rights, in higher education governance.

|  |  |  |
| --- | --- | --- |
| **Time** | **Roadmap** | **San Marino’s implementation plan** |
| By 1 June 2021 | Establish a timetable and develop an overview of measures required to modify current arrangement |  |
| By 1 June 2022 |  | First draft of the new University law |
| By 1 January 2023 |  | Start of the legislative process |
| By 1 November 2023 | Submission of the required legislative measures to Parliament | Adoption of the new law |

#### Lifelong learning/ social dimension of higher education

|  |  |  |
| --- | --- | --- |
| **Time** | **Roadmap** | **San Marino’s implementation plan** |
| By 1 June 2021 | develop a plan and timetable for stimulating the participation of underrepresented groups in higher education |  |
| January 2022 |  | A working group will start an assessment of specific needs and possible amendments |
| By 1 November 2023 | Take measures to stimulate participation of underrepresented groups. If these require legislative amendments submit them to Parliament. | New University law |

## 3. Meeting plan for the WG

Meeting times may be specified in accordance with the BFUG meeting schedule to enable the working group to report on progress in implementation to the BFUG and BFUG board.

|  |  |
| --- | --- |
| **Time and place** | **Tasks** |
| 17 May 2021, online | Establish a timetable for the implementation of the San Marino Roadmap |
| 10-11 November 2021, San Marino | Update on the implementation in San Marino, discussions and peer learning with Sammarinese stakeholders, identification of possible support measures needed |
| January 2022, online | Peer support sessions on quality assurance and on university governing models |
| March 2022, online | Update on the implementation in San Marino, feedback on peer support sessions |
| September-October 2022 | Update on the implementation in San Marino, peer learning and support activities, analysis of progress in the implementation of the Roadmap |
| February-March 2023 | Update on the implementation in San Marino, analysis of progress in the implementation of the Roadmap |
| September-October 2023 | Follow-up on the implementation, first draft of the final report of the WG for discussion. |
| December 2023 -January 2024 | Conclusions and final report of the WG for the BFUG |