## Slide 2: Workplan 2021-2024 with the timeline of key activities
Nino S. Schmidt
Co-Chair of the BFUG Working Group on Social Dimension 2021-2024
Institute for the Development of Education (IDE), Executive Director
Zagreb, Croatia
BFUG Working Group on Social Dimension 2021-2024, 1st on-line meeting, 8.7.2021.

## Slide 3: Workplan for 2021: objectives
Finalizing Workplan 2021-2022 at the 2nd meeting of the WG SD
Peer-learning activities and examples of best practices on the implementation of the Principles
Discussion on indicators and benchmarks for the Principles
Discussion on a system of monitoring the implementation of the Principles
2nd on-line meeting in October 2021: Friday 8 October 2021
3rd on-line meeting in November 2021: Friday 19 November 2021

## Slide 4: Workplan for 2021: dates and objectives
2nd on-line meeting in October 2021: Friday 8 October 2021
before the BFUG Board meeting on 21 October 2021
Finalizing Workplan 2021-2024
Peer-learning activities and examples of best practices on the implementation of the Principles:
  Principle No.4 on reliable dana: New Eurostudent VII results and plans for the Eurostudent VIII
  Principle No.8 on inclusive mobility: presentation of the ‘Inclusive Mobility EU Platform’ – toolbox, self-assesment tool
  Other proposals?
Discussion on indicators and benchmarks for the Principles

## Slide 5: Workplan for 2021: dates and objectives
3rd on-line meeting in November 2021: Friday 19 November 2021
before the BFUG meeting on 1-2 December 2021
Peer-learning activities and examples of best practices on the implementation of the Principles:
  Principle No.9 on community engagement:
    TEFCE Toolbox for the Community Engagement in HE
    Critical reflection of univerisites that implement the TEFCE Toolbox
    Other stakeholders active in this field: Council of Europe
  European Commission update on the Higher Education Transformation Agenda (forthcoming)
  Other proposals?
Discussion on indicators and benchmarks for the Principles

## Slide 6: Workplan for 2022: objectives
Finalizing Workplan 2022-2024
Peer-learning activities and examples of best practices on the implementation of the Principles
Discussion on indicators and benchmarks for the Principles
Discussion on a system of monitoring the implementation of the Principles

## Slide 7: Workplan for 2022: dates and objectives
4th meeting in February 2022 (date TBC in November 2021)
5th meeting in April 2022 (date TBC in November 2021)
6th meeting in June 2022 (date TBC in November 2021)
Finalizing Workplan 2022-2024
Peer-learning activities and examples of best practices on the implementation of the Principles:
  Proposals?
Discussion on indicators and benchmarks for the Principles
Discussion on a system of monitoring the implementation of the Principles

## Slide 8: Resources and methods of work
Web site for the WG on SD at the www.ehea.info:
Key documents related to the work of the WG SD
Documents related to the WG-meetings
Useful resources: literature, policy briefs, information on useful projects etc.
Methods of work:
Questionnaires for collecting ideas for the PLAs
Communication via the BFUG Secretariat secretariat@ehea.info
Communication via Co-chairs: nscukanec@iro.hr and martina.darmanin@esu-online.org

## Slide 9: Thank you for your attention!
Ninoslav Šćukanec Schmidt
Co-Chair of the BFUG Working Group on Social Dimension 2018-2020
Institute for the Development of Education (IDE)
Zagreb, Croatia
nscukanec@iro.hr
www.iro.hr
BFUG Working Group on Social Dimension:
http://www.ehea.info/page-Advisory-Group-1
EHEA Ministerial Conference Rome 2020 – 19 November 2020 (9-17h):
http://www.ehea.info/index.php
https://ehea2020rome.it/