Draft Timetable of Bologna WG Recognition

| Timing | Event | Actions |
| --- | --- | --- |
| 15/02/ 2010 | WG meeting (Brussels) | Discussion of Terms of Reference of the Working group, setting road map and timetable |
| Mar-May/2010 |  | Gathering ideas from WG members, consultations with stakeholders |
| 10/06/2010 | WG meeting (Strasbourg) | Brainstorming on possible recommendations |
| 21-22/ 06/2010 | ENIC-NARIC meeting | Discussion of all issues with ENIC and NARIC networks, gathering opinions and information |
| Jul-Oct/2010 |  | Preparing first drafts of recommendations |
| 24-25/ 08/2010 | BFUG meeting | Intermediate reporting to BFUG |
| Oct-Nov/2010 | WG meeting (Location?) | Discussing and revising first draft of recommendations |
| Nov 2010-Jan 2011 |  | Preparing documents and organising for a stakeholder meeting |
| Feb/Mar 2011 | WG and Stakeholder meeting – conference? Seminar? (Location? sponsors? Perhaps attached to BFUG?) | Discussing issues and draft recommendations with policy makers, recognition specialists, HEIs, QA agencies etc. |
| 17-18/ 03/2011 | BFUG meeting | Intermediate reporting to BFUG |
| Apr-May 2011 |  | Finalising drafts |
| Jun 2011 | WG meeting (attached to ENIC/NARIC?) | Approval of recommendations by WG |
| Autumn 2011 | BFUG meeting | Submission of recommendations to BFUG |