Work plan 2010 -2012							updated 30 March 2011

| Date | Action | Content |
| --- | --- | --- |
| 13 January 2010 | WG Meeting Berlin | 20% benchmark data issues agree on work plan |
| 12 May 2010 | WG Meeting Berlin | If necessary, review Work plan after Budapest/Vienna conference Discuss elements of mobility strategy Agree on survey to be sent out to BFUG members on mobility obstacles, good practice examples for increasing mobility and for encouraging a balanced flow of mobility (together with reporting group/as a separate exercise?) |
| 30 September 2010 | Deadline for country replies to mobility questionnaire |  |
| 4 November 2010 | WG Meeting Budapest | Discussion on results of questionnaire and ACA mobility data Develop recommendations |
| 31 January 2011 | First draft of Mobility strategy to be sent to WG members |  |
| 21 February 2011 | Comments by WG members |  |
| 16 March 2011 | Second draft of Mobility strategy to be sent to WG members |  |
| 17-18 March 2011 | BFUG meeting Budapest |  |
| 28-29 March 2011 | DAAD Seminar “From Imbalanced to Balanced Mobility in the EHEA – Current Challenges and Perspectives for the Future” |  |
| 29-30 March 2011 | WG Meeting Berlin | Discuss draft of Mobility strategy Discuss input from DAAD seminar and other mobility seminars |
| 24 August 2011 | WG Meeting in Berlin (before BFUG Board meeting in Armenia, 6-7 September 2011) | Agree on EHEA Mobility strategy |
| 13-14 October 2011 | BFUG Meeting in Cracow | Presentation of draft EHEA Mobility strategy |
| 26-27 April 2012 | Ministerial Conference Bucharest | Endorsement/Adoption of EHEA Mobility strategy |