Timeline for the production of the integrated report

on the implementation of the Bologna Process

- as on 7th of July 2011 -

| 2010 | Ongoing Eurostat data collection | Eurostudent data collection |
| --- | --- | --- |
| 21 January | WG Reporting: Approve draft outline of the integrated report and timeline to be presented to the BFUG in Madrid on 18-19 February 2010. |  |  |
| 18-19 February | BFUG: approval of main orientation of the integrated report & the timeline for preparing it |  |  |
| February – August | Definition of indicators and development of questionnaire by Eurydice, Eurostat and Eurostudent |  |  |
| 16 June | WG Reporting: discussion of format of the integrated report and of draft questionnaire |  |  |
| 24-25 August | BFUG: approval of the plans for preparing the 2012 Report and comments on the questionnaire |  |  |
| September | Data collection by Eurydice through the questionnaire which will be filled by BFUG representatives in consultation with national stakeholders - mobility part |  |  |
| September-December | Pre-test of questionnaire by Eurydice |  |  |
| 16 November | WG Reporting: finalisation of questionnaire prepared by Eurydice; discussion and preliminary approval of selection of indicators |  |  |
| 2011 |  |  |
| January – April | Data collection by Eurydice through the questionnaire which will be filled by BFUG representatives in consultation with national stakeholders Data collection by Eurostat of statistical information from countries of the EHEA not participating in the regular data collections |  |  |
| May- November | Analysis of material, drafting of integrated report, integrating data from Eurostat, Eurostudent and Eurydice and consultation with the relevant working groups |  |  |
| 1 July | WG Reporting: first discussion of the structure of the implementation report, draft Chapter on Social dimension and scorecard indicators. |  |  |
| 13-14 October | BFUG meeting in Krakow: presentation of the scorecard indicators, of the progress; informing the BFUG on the possible new indicators needed for the future. |  |  |
| 3 November | WG Reporting: Second discussion on the draft integrated report and development of recommendations and conclusions. |  |  |
| End of year | Draft integrated report and conclusions to be sent to BFUG |  |  |
| 2012 |  |  |
| January (exact date tbc) | BFUG: discussion of draft integrated report and of the conclusions prepared by the WG Reporting in October |  |  |
| March | Print-ready electronic version of the integrated report provided to BFUG |  |  |
| 26-27 April | Presentation of final integrated report to the ministerial conference |  |  |